## Sheet
Salno | Seq name/Reel | Shot list | Descriptions | Frames | EXR FRAMES | Ref | Shot Type | SCAN STATUS | COMPLEXITY | MASTER | CMM STATUS | ROTO | Gap comment | Layout status | Expected End Date
001 | REEL_01 | SH_010 | Hero character jumps over the car | 1001 | 1050 |  | VFX | RECEIVED | P1 | MASTER | WIP | Roto needed for leg | None | Done | 2024-12-20
002 | REEL_01 | SH_020 | Car explosion background | 1001 | 1120 |  | FULL CG | RECEIVED | P2 | MASTER | APPROVED |  | Final | Final | 2024-12-18
003 | REEL_02 | SH_005 | Dialogue scene cleanup | 1001 | 1090 |  | VFX | Pending | P1 | MASTER | Awaiting approval | Wire removal |  | WIP | 2024-12-25
004 | REEL_02 | SH_015 | Spaceship landing | 1001 | 1200 |  | FULL CG | RECEIVED | P2 | MASTER | Kickback | Fix reflection | Missing textures | Done | 2024-12-22
005 | REEL_03 | SH_030 | Forest environment extension | 1001 | 1150 |  | VFX | RECEIVED | P1 | MASTER | YTS |  |  | Done | 2024-12-21